## Work Plan
Task: | Task Description: | Task Breakdown: | Team Member: | Due Date:
Connect Database | Connect database to the website | - - -
Finalize Desgin | Finsih the desgin with bootstrap | - - -
Admin Section | Section where Rod will be able to manage the website and it's contents | - - -
Security | Security conponet - vaild reseacrchers to request and gain access to database/website | - Reseach if there is a database or form of id for researchers - -
Progress Report | Milestone 7: Provide an update on progress | - Would be a good time to meet with client about progress - - | Team Lead: Theo | 2020-11-17
Final Presentation | Milestone 8: Present | - - - | Team Lead: Avash | 2020-12-16
*Will be updating this document when we meet as a group tommorrow* 10-28
Will also be updating the project document once this work plan is done. -Sam